## Project
Project Overview
Project Name
Project Manager
Description
Start date (read-only) | 2025-06-02
Finish date (read-only) | 2025-06-27
Duration (read-only) | Pro only
Progress (read-only) | 100%
Work (read-only) | Pro only
Cost (read-only) | Pro only

## Tasks
[6 empty] | June 2025 | [28 empty] | July 2025 | [30 empty] | August 2025 | [30 empty] | September 2025 | [29 empty] | October 2025
10 | WBS | ACTIVIDAD | COMIENZO | FIN | PROGRESO | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
[6 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
1 | 1 | Estudio preliminar | 2025-06-02 | 2025-06-02 | 100% | bar: Mo; Mo
2 | 2 | Desarrollo de modulo de carga | 2025-06-03 | 2025-06-12 | 100% | bar: Tu to Th; Mo
10 | 3 | Construcción de una interfaz web básica | 2025-06-03 | 2025-06-12 | 100% | bar: Tu to Th; Mo
3 | 4 | Aplicación de técnicas de preprocesamiento | 2025-06-13 | 2025-06-22 | 100% | bar: Fr to Mo
4 | 5 | Implementación del motor OCR | 2025-06-13 | 2025-06-22 | 100% | bar: Fr to Mo
5 | 6 | Diseño de la estructura de salida | 2025-06-13 | 2025-06-22 | 100% | bar: Fr to Mo
7 | 7 | Realización de pruebas | 2025-06-23 | 2025-06-27 | 100% | bar: Mo to Fr
8 | 8 | Documentación técnica del sistema | 2025-06-23 | 2025-06-27 | 100% | bar: Mo to Fr